## Defect log
Lab 4 | Defect log
ID | Defect | Severity* | Priority* | Fix | Test result | Current status
D01 | format_task_report ID 1 causes a TypeError. | Major | P2 | Use an f-string to format the report. Expected: Task #1: Study. | Before: Failed After: Passed | Verified
D02 | build_query Bob's task causes a SQL error. | Major | P2 | Use a placeholder and parameters. Update the caller to pass both. | Before: Failed After: Passed | Verified
| *Suggested: Major means the feature fails for normal input. |  |  | P2 means fix during the current lab work.
| Defect lifecycle |  |  | Draft stage history
ID | New | Triaged | Assigned | Fixed | Verified | Closed
D01 | Failing test recorded | Major / P2 | Student (proposed) | Report formatting fixed (reconstructed) | Test passed | Pending review
D02 | Failing test recorded | Major / P2 | Student (proposed) | SQL parameters used (reconstructed) | Test passed | Pending review
| Review the suggested severity, priority and assignment. |  |  | Mark Closed when your review and evidence are complete.
| Evidence: retain the genuine failing and passing outputs. |  |  | Latest combined run: 11 passed in 1.15 seconds.